i have build a foundation of construction work program modul as part of our work diary platform. we intend to shape this modul as the bridge or check balance between diary entry (which is physical work at site, our main strength) vs actual work program widely used by project manager (MS Project, Primavera) and not intended to replace them. our modul import csv files from these software and set baseline which may have multiple version. can you write guideline for this modul ?

It sounds like you’ve identified a brilliant "missing link" in construction tech. Most project managers struggle with the "truth gap"—the distance between a pristine Gantt chart in the office and the messy reality of the site.

By positioning your module as the bridge, you aren't fighting for the PM’s desktop; you’re becoming the lens through which they see if their plan is actually surviving contact with reality.

Here is a structured guideline designed to help your users navigate this module effectively.

Guideline: The Construction Work Program (CWP) Module

Objective

To provide a real-time Check & Balance between the theoretical schedule (MS Project/Primavera) and the physical truth recorded in the Daily Work Diary.

1. Data Integration & Baseline Management

The foundation of this module is the "Import & Freeze" workflow. Since we do not edit the logic here, we ensure the integrity of the Project Manager’s original plan.

- Importing Schedules: Use the .csv export function from MS Project or Primavera P6. Ensure columns for Task Name, Start/Finish Dates, and unique ID (WBS) are mapped correctly.

- Version Control (Baselines):

  - Baseline 0: Your original contract program.

  - Revised Baselines: When a major Extension of Time (EOT) is granted, import a new version.

  - The "Active" Toggle: Only one baseline can be "Active" for diary comparison at a time to prevent data fragmentation.

2. The Bridge: Linking Diary to Task

For the "Check & Balance" to work, site activities must "talk" to the program tasks.

- Task Tagging: When a supervisor creates a diary entry, they should tag the relevant WBS Task from the imported program.

- Physical Progress vs. Duration:

  - The Program tracks time elapsed.

  - The Diary tracks work done (e.g., "50m³ of concrete poured").

  - The Goal: If the program says a task is 50% through its duration, but the diary shows only 20% of the volume is installed, the module flags a variance.

3. Monitoring the "Truth Gap"

Use the module to visualize the discrepancies between the office and the field.

- Planned vs. Actual (P v A): Automatically generate a "S-Curve" or a simplified Gantt view that overlays the imported CSV bars with a progress bar fueled by daily diary entries.

- Early Warning System (EWS): If a task has no diary entries for 3 consecutive days despite being "Active" in the program, the system should trigger a "Stagnant Task" alert.

4. Best Practices for Users

To get the most out of this module, follow these "Golden Rules":

| Feature | Do | Don't |
| --- | --- | --- |
| Importing | Clean your CSV in MS Project first to remove empty rows. | Try to manually build a 1,000-line schedule inside this module. |
| Diary Entry | Be specific. Link the diary to the lowest level of the WBS (Sub-tasks). | Link "Everything" to a high-level summary header. |
| Baselines | Create a new version for every major project milestone change. | Overwrite your original Baseline 0. |

5. Technical Logic: The Comparison Formula

The module calculates the health of a task using a basic variance logic:

Variance=%Planned Progress-%Physical Progress (from Diary)

- Positive Variance: Site is ahead of the office plan.

- Negative Variance: Site is lagging; the PM needs to update the MS Project file.

How this helps the Project Manager

Instead of waiting for a weekly meeting to find out a task is behind, the PM can see the Daily Validation. If the MS Project file says "Excavation" should be finished, but the Work Diary shows "Rain - No Work," the bridge immediately highlights the need for a program update or a delay claim.

we need to have a solid guideline and calculation for Planned % and Actual%. when we talking about huge project, the WBS depth level will change the way the parent and children of the WBS % is calculated. the weight of the task depend on certain criteria. include this in our document and find the models to be used for this calculation

To handle deep WBS (Work Breakdown Structure) hierarchies in large-scale construction, you cannot rely on simple averages. A 1-day task cannot carry the same "weight" as a 30-day task.

To make your module a robust "check and balance," you must implement a Weighted Progress Model. This ensures that the progress of a parent WBS element accurately reflects the significance of its children.

1. The Weighting Logic

Before calculating percentages, every task must be assigned a Weight (W). This represents the task's "value" relative to the whole project.

Selection of Weighting Criteria

You should allow the user to choose one of three models during the CSV import:

- Duration-Based: Weight is determined by the number of working days. (Most common for general scheduling).

- Cost-Based: Weight is determined by the budgeted cost of the task. (Best for financial tracking).

- Man-Hour Based: Weight is determined by the labor effort required. (Best for resource-heavy projects).

2. Calculation Models

A. Planned % (The Office Baseline)

This is calculated based on the Current Date (Data Date) relative to the Baseline Start and Finish dates imported from MS Project/Primavera.

For an individual task:

Planned%=Data Date-Baseline StartBaseline Duration×100

(Clamped between 0% and 100%)

B. Actual % (The Site Truth)

This is driven by the Work Diary. Unlike the planned %, this is entered by the site team based on "Physical Percent Complete."

- Fixed Formula:

Actual%=Total Quantity Installed to DateTotal Forecast Quantity

- Milestone Formula: 0% (Not Started), 50% (In Progress), 100% (Completed).

3. WBS Roll-up (Parent-Child) Logic

This is where the "Check & Balance" happens. To calculate the percentage of a Parent WBS, use the Weighted Average of its children, not a simple average.

The Model:

The percentage for a Parent (P) is the sum of the weighted progress of its Children (𝑐):

Parent %=i=1nChild %i×Wi∑Wchildren

Example Scenario:
A Parent WBS "Foundations" has two tasks:

- Task A (Mass Pour): 10 days duration (Weight = 10) -> 80% Complete

- Task B (Curing): 2 days duration (Weight = 2) -> 0% Complete

Simple Average: (80+0)/2=𝟒𝟎%(Misleading)
Weighted Average: (80%×1012)+(0%×212)=𝟔𝟔.𝟔%

(Accurate representation of effort)

4. Implementation Guidelines for the Module

Step 1: Define Weighting on Import

Upon CSV import, the module must ask: "Which column defines the weight of tasks?"

- If the user selects "Duration," the system automatically calculates 𝑊

using Finish - Start.

Step 2: The "Depth-First" Roll-up

The system must calculate from the "leaves" (lowest level tasks) upward.

- Calculate Actual % for Level 4.

- Roll up to Level 3 using weights.

- Roll up to Level 2.

- Final Project % at Level 1.

Step 3: Handling Variance (The Check & Balance)

Once the Parent Planned % and Parent Actual % are calculated, the module displays the Schedule Variance (SV):

𝑆𝑉=𝐴𝑐𝑡𝑢𝑎𝑙%−𝑃𝑙𝑎𝑛𝑛𝑒𝑑%

- Warning (Yellow): −5%>𝑆𝑉>−10%

- Critical (Red): 𝑆𝑉<−10%

(The site is significantly behind the PM's schedule).

5. Summary Table for Users

| Level | Calculation Type | Data Source |
| --- | --- | --- |
| Leaf Task (Bottom) | Discrete Value | Manual Diary Entry / Quantity Tracking |
| Parent WBS | Weighted Aggregate | Sum of (Child % × Child Weight) |
| Grand Total | Project Health | Sum of all Level 1 Weighted Percentages |

is there available a combo of Weighting Criteria of Duration-Based, Cost-Based and Man-Hour Based. so that user can have multi selection. and can ms project and primavera export man hour and cost? i am sure duration can be exported

Yes, you can absolutely offer a multi-selection combo of weighting criteria. This approach, often called Blended Normalization, provides a more balanced view by preventing any single factor (like duration) from skewing the perceived progress of the project.

1. Multi-Selection Model (Blended Weighting)

When a user selects multiple criteria, you calculate a Blended Weight (𝑊𝐵) for each task. This is the average of the relative weights from each selected category.

The Blended Formula:
For any task 𝑖, if a user selects Duration (𝐷), Cost (𝐶), and Man-hours (𝑀):
WB,i=WeightD,iWeightC,iWeightM,i3

- Normalizing the Inputs: Before averaging, you must convert each raw value into a percentage of the project total for that category (e.g.,

WeightC,i=CostiTotal Project Cost

) so you aren't adding "apples to oranges".

- Result: This blended weight is then used in your parent WBS roll-up calculation.

2. Software Export Capabilities

Both MS Project and Primavera P6 can export the required data to CSV or Excel formats.

- MS Project:

  - Duration: Exported by default.

  - Cost: Can export Total Cost or Budgeted Cost fields.

  - Man-Hours: Export the Work field (expressed in hours).

  - Note: You must use the "Export Wizard" in MS Project to map these specific fields to your CSV columns.

- Primavera P6:

  - Duration: Exported as "Original Duration" or "At Completion Duration".

  - Cost: Export "Budgeted Total Cost" or "At Completion Total Cost".

  - Man-Hours: Export "Budgeted Labor Units" or "Planned Labor Units".

  - Tip: P6 is highly flexible; you can customize the "Activity Table" columns to include exactly these three fields and then use the Spreadsheet (XLSX) or CSV export option.

3. Recommended Implementation Logic

- Selection: User toggles on "Duration," "Cost," and/or "Man-Hours" in your module.

- Mapping: User maps their CSV columns to these three types.

- Automatic Weighting: Your system calculates the relative weight for every leaf task based on the selection.

- Verification: Ensure the sum of all leaf task weights equals 100% (or 1.0) before proceeding with the % Actual calculation.

Module Guideline: Construction Work Program Bridge

1. Executive Summary

The Work Program Module is a validation layer. It does not replace the Project Manager’s scheduling tools; instead, it imports their data (via CSV) to compare the "Plan" against the "Physical Reality" recorded in the Work Diary.

2. Data Integration (The Baseline)

To maintain a consistent "Check & Balance," the module uses a structured import process:

- Supported Imports: CSV/XLSX exports from MS Project and Primavera P6.

- Version Control: Supports multiple baselines (Baseline 0, Revision 1, etc.).

- The Active Baseline: Only one version is "Active" at a time to drive the Planned % vs. Actual % comparison.

- Data Mapping:

  - Duration: Maps to Original Duration.

  - Cost: Maps to Budgeted Total Cost.

  - Man-Hours: Maps to Planned Labor Units/Work.

3. Progress Calculation Models

A. Planned % (The Office Plan)

Calculated automatically based on the Current Date (Data Date) relative to the imported Baseline dates.

- Formula:

Planned%=clampCurrent Date-Baseline StartBaseline Duration0100

B. Actual % (The Site Truth)

Driven by supervisors via the Work Diary.

- Physical Progress: Based on quantities installed (e.g., m3 of concrete) or manual % complete updates for specific tasks.

4. The Weighting & Roll-up Model

For large-scale projects with deep WBS levels, the module uses Weighted Progress to ensure parent tasks accurately reflect the significance of child tasks.

Multi-Selection Weighting Criteria (Blended Normalization)

Users can select one or a combination of three criteria to determine a task's "importance" in the project:

- Duration-Based: Longer tasks carry more weight.

- Cost-Based: High-value tasks carry more weight.

- Man-Hour Based: Resource-intensive tasks carry more weight.

The Blended Weight Formula (WB)

If a user selects multiple criteria, the system calculates a Normalized Average:

WB,i=WDurationWCostWManHoursN

(Where 𝑁 is the number of criteria selected).

5. WBS Hierarchy Logic (Parent-Child)

The module calculates progress from the "Bottom-Up" (Leaf tasks to Project Summary).

The Parent Roll-up Formula:
The percentage for a Parent WBS (𝑃) is the sum of the weighted progress of its Children (𝑐):

Parent %=i=1nChild %i×WB,i∑WB,children

6. The "Check & Balance" (Variance)

The primary output of the module is the Schedule Variance (SV). This identifies the "Truth Gap":

SV=Actual%-Planned%

| Variance Range | Status | Action Required |
| --- | --- | --- |
| +5% and above | 🟢 Ahead | Site is outperforming the office plan. |
| 0% to -5% | 🟡 On Track | Normal minor fluctuations. |
| -5% to -10% | 🟠 Warning | Site lagging; check for resource bottlenecks. |
| Below -10% | 🔴 Critical | PM must update the MS Project/P6 file or file an EOT. |

7. Exporting Data for Integration

To ensure a smooth bridge, users should export the following fields from their scheduling software:

- MS Project: Use the "Export Wizard" to select Task Name, Start, Finish, Work (for Man-Hours), and Cost.

- Primavera P6: Use "Spreadsheet Export (XLSX)" to select Activity ID, Name, Planned Start/Finish, Budgeted Total Cost, and Budgeted Labor Units.

8. Best Practices

- Linkage: Always tag Daily Diary entries to the lowest-level WBS (Leaf Tasks).

- Cleaning: Ensure the CSV is "Clean" (no empty rows or summary-only exports) before importing.

- Regular Sync: Import a revised baseline whenever a major change order is approved to keep the "Check & Balance" relevant.